## Product Backlog
Requirements | Started | Completed By | Completed?
View Resturant | 2020-11-17 | 2020-11-22 | Yes
Filter Resturants | 2020-11-22 | 2020-11-29 | Yes
Pick a Random Resturant | 2020-11-27 | 2020-11-29 | Yes
Get Resturants from External Datasource | 2020-11-27 | 2020-11-29 | Yes
View Resturant Reviews | 2020-11-27 | 2020-11-29 | Yes
Get Resturant Reviews from External Datasource | 2020-11-27 | 2020-11-29 | Yes

## Burnchart Data
|  | Dates | Total Time | Remaining Effort: | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30
Total Work Hours | 46.5 | 2020-11-16 | 46.5 | Total Time: | 46.5 | 46.5 | 46.5 | 46.5 | 44.5 | 41.5 | 39.5 | 36.5 | 33.5 | 33.5 | 20 | 14 | 6 | 1 | 0
Ideal Remaining Work Hours | 43.1786 | 2020-11-17 | 46.5
Ideal Remaining Work Hours | 39.8571 | 2020-11-18 | 46.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Remaining Work Hours | 36.5357 | 2020-11-19 | 46.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Remaining Work Hours | 33.2143 | 2020-11-20 | 44.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Remaining Work Hours | 29.8929 | 2020-11-21 | 41.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Remaining Work Hours | 26.5714 | 2020-11-22 | 39.5 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Remaining Work Hours | 23.25 | 2020-11-23 | 36.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Remaining Work Hours | 19.9286 | 2020-11-24 | 33.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Ideal Remaining Work Hours | 16.6071 | 2020-11-25 | 33.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Ideal Remaining Work Hours | 13.2857 | 2020-11-26 | 20 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Remaining Work Hours | 9.9643 | 2020-11-27 | 14 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Ideal Remaining Work Hours | 6.6429 | 2020-11-28 | 6 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Ideal Remaining Work Hours | 3.3214 | 2020-11-29 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Ideal Remaining Work Hours | 0 | 2020-11-30 | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
[5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0
[5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
[5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
[5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
[5 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Backlog
Backlog Item | Time to Deliver (hrs) | Time Completed (hrs) | Time Left (hrs) | Date Completed | Assigned | Completed?
Create Resturant Data Class, Getters, and Constructor | 0.5 | 1 | 0 | 2020-11-20 | Alex | Yes
Testing Resturant Data Class | 0.5 | 1 | 0 | 2020-11-20 | Alex | Yes
Create Resturant Manager | 0.5 | 1 | 0 | 2020-11-20 | Alex | Yes
Test Resturant Manager | 0.5 | 1 | 0 | 2020-11-20 | Alex | Yes
Create Resturant View Model | 1 | 0.5 | 0 | 2020-11-21 | Furichous | Yes
Test Resturant View Model | 1 | 0 | 0 | 2020-11-22 | Furichous | Yes
Create Enum for Price | 0.5 | 0.2 | 0 | 18-Nov-2020 | Alexander | Yes
Test Enum for Price | 0.5 | 0.2 | 0 | 19-Nov-2020 | Alexander | Yes
Make FXML GUI | 2 | 2 | 0 | 2020-11-21 | Alexander | Yes
Make Query Abstract Class | 0.5 | 0.5 | 0 | 2020-11-26 | Furichous | Yes
Make Review Query | 1 | 1 | 0 | 2020-11-26 | Furichous | Yes
Make Restaurant Query | 1 | 1 | 0 | 2020-11-26 | Furichous | Yes
Make JSONLoader | 3 | 3 | 0 | 2020-11-26 | Furichous | Yes
Make Query Manager | 2 | 2 | 0 | 2020-11-26 | Furichous | Yes
Make Scene Controller | 2 | 2 | 0 | 2020-11-26 | Furichous | Yes
Make BaseCodeBehind | 1 | 1 | 0 | 2020-11-26 | Furichous | Yes
Add functionality to Main | 1 | 1 | 0 | 2020-11-28 | Furichous | Yes
Make Review Class | 1 | 1 | 0 | 2020-11-22 | Alex | Yes
Make Review Manager Class | 1 | 1 | 0 | 2020-11-24 | Alex | Yes
Test Review Class | 2 | 1 | 0 | 2020-11-23 | Alex | Yes
Test Review Manager Class | 2 | 1 | 0 | 2020-11-24 | Alex | Yes
Make Reviews View Model | 1 | 1.5 | 0 | 2020-11-26 | Alex | Yes
Test Reviews View Model | 2 | 2 | 0 | 2020-11-27 | Alex | Yes
Make Reviews Code Behind | 1 | 1 | 0 | 2020-11-28 | Alex | Yes
Research How to Dynamically Add Reviews to The GUI | 3 | 1 | 0 | 2020-11-28 | Alex | Yes
Make FXML for Location and Radius Page | 1 | 0.5 | 0 | 2020-11-23 | Alexander | Yes
Make FXML for Filtering Page | 1.5 | 0.4 | 0 | 2020-11-26 | Alexander | Yes
Make CodeBehind for Filter | 3 | 2 | 0 | 2020-11-29 | Alexander | Yes
Make ViewModel for Filter | 3 | 2 | 0 | 2020-11-27 | Alexander | Yes
Test the FilterViewModel | 3 | 1 | 0 | 2020-11-28 | Alexander | Yes
Make FXML for No Restaurants Found Error Page | 1 | 0.5 | 0 | 2020-11-27 | Alexander | Yes
Make and Test Radius Enum | 0.5 | 0.5 | 0 | 2020-11-26 | Alexander | Yes
Make Welcome CodeBehind and FXML | 1 | 0 | 0 | 2020-11-29 | Alexander | Yes
Make Reviews Error Code Behind and FXML | 1 | 0.5 | 0 | 2020-11-29 | Alexander | Yes